## Sheet1
Description | 2022 | [11 empty] | 2023 | [11 empty] | 2024
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Project start
Milestones - original
Package A
Assessment of the multiple hydroclimatic conditions of chronic and flash droughts and dry spell dynamics for the Spree Catchment and Berlin
Projections of dry and plant stress periods and water excess periods in the Spree catchment and across the urban agglomeration of Berlin to be used for rainwater harvesting modelling
Package B
Development of rainwater harvesting modelling scenarios options under different dry spell and flash drought conditions
Assessment of demand, maximal extent and optimization of water availability by regulating water deficit and excess
Reliability projections of in situ and ex situ rainwater harvesting options for rural sites in the Spree catchment and across the urban sprawl of Berlin
Milestones - personal
Submission paper 1 - drought changes
Submission paper 2 - impact driven definitions
Submission paper 3 - flash drought definitions (impact based)
Submission paper 4 - water harves demand